## Welcom Screen
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-WEL-001 | Verify Welcome Screen is displayed after ATM startup | ATM launched | Start ATM application | N/A | Welcome Screen displayed successfully | High | Welcome Screen displayed successfully | Pass
TC-WEL-002 | Verify Bank MASR title is displayed | Welcome Screen opened | Observe screen | N/A | Bank MASR title displayed correctly | Medium | Title displayed correctly | Pass
TC-WEL-003 | Verify welcome message is displayed | Welcome Screen opened | Observe screen | N/A | Welcome message displayed correctly | Medium | Message displayed correctly | Pass
TC-WEL-004 | Verify Login button is displayed | Welcome Screen opened | Observe screen | N/A | Login button displayed | High | Login button displayed | Pass
TC-WEL-005 | Verify Help button is displayed | Welcome Screen opened | Observe screen | N/A | Help button displayed | High | Help button displayed | Pass
TC-WEL-006 | Verify Login button is clickable | Welcome Screen opened | Click Login | N/A | User navigates to PIN Entry Screen | Critical | User navigated successfully | Pass
TC-WEL-007 | Verify Help button is clickable | Welcome Screen opened | Click Help | N/A | User navigates to Help Screen | High | User navigated successfully | Pass
TC-WEL-008 | Verify Welcome Screen layout loads correctly | Welcome Screen opened | Observe UI | N/A | No broken UI elements displayed | Medium | Layout displayed correctly | Pass
TC-WEL-009 | Verify Welcome Screen loads within performance requirement | ATM running | Launch application | N/A | Screen displayed within 3 seconds | Medium | Screen loaded within 3 seconds | Pass
TC-WEL-010 | Verify Welcome Screen language is formal and polite | Welcome Screen opened | Review text | N/A | All displayed text is formal and professional | Low | Language is formal and polite | Pass

## Help Screen
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-HLP-001 | Verify Help Screen opens successfully | Welcome Screen displayed | Click Help | N/A | Help Screen displayed | High | Help Screen displayed | Pass
TC-HLP-002 | Verify ATM usage instructions are displayed | Help Screen opened | Review instructions | N/A | Usage instructions displayed | High | Instructions displayed correctly | Pass
TC-HLP-003 | Verify first guidance section is displayed | Help Screen opened | Scroll page | N/A | Login instructions displayed | Medium | Instructions displayed | Pass
TC-HLP-004 | Verify second guidance section is displayed | Help Screen opened | Scroll page | N/A | PIN instructions displayed | Medium | Instructions displayed | Pass
TC-HLP-005 | Verify third guidance section is displayed | Help Screen opened | Scroll page | N/A | Withdrawal instructions displayed | Medium | Instructions displayed | Pass
TC-HLP-006 | Verify fourth guidance section is displayed | Help Screen opened | Scroll page | N/A | Deposit instructions displayed | Medium | Instructions displayed | Pass
TC-HLP-007 | Verify animated guidance content is displayed | Help Screen opened | Observe GIF area | N/A | GIF guidance displayed successfully | Medium | GIF displayed correctly | Pass
TC-HLP-008 | Verify Back button is displayed | Help Screen opened | Observe screen | N/A | Back button displayed | Medium | Back button displayed | Pass
TC-HLP-009 | Verify Back button navigation | Help Screen opened | Click Back | N/A | User returns to Welcome Screen | High | User returned successfully | Pass
TC-HLP-010 | Verify Help Screen content readability | Help Screen opened | Review text | N/A | Instructions are readable and understandable | Low | Content readable | Pass
TC-HLP-011 | Verify Help Screen loads within 3 seconds | Welcome Screen displayed | Open Help Screen | N/A | Screen displayed within 3 seconds | Low | Screen loaded within 3 seconds | Pass

## Auth Module
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-AUTH-001 | Verify PIN Entry Screen is displayed | Click Login | Navigate to PIN screen | N/A | PIN Entry Screen displayed | Critical | Screen displayed | Pass
TC-AUTH-002 | Verify numeric keypad is displayed | PIN Screen opened | Observe keypad | N/A | Digits 0-9 displayed | High | Keypad displayed | Pass
TC-AUTH-003 | Verify Enter button is displayed | PIN Screen opened | Observe keypad | N/A | Enter button displayed | High | Enter button displayed | Pass
TC-AUTH-004 | Verify Delete button is displayed | PIN Screen opened | Observe keypad | N/A | Delete button displayed | High | Delete button displayed | Pass
TC-AUTH-005 | Verify Return Card button is displayed | PIN Screen opened | Observe screen | N/A | Return Card button displayed | Medium | Button displayed | Pass
TC-AUTH-006 | Verify successful PIN validation | Valid PIN exists | Enter valid PIN and submit | 1234 | System navigates to Password Screen | Critical | Navigation successful | Pass
TC-AUTH-007 | Verify invalid PIN error message | PIN Screen opened | Enter invalid PIN | 9999 | ERR-001 displayed | Critical | Correct error displayed | Pass
TC-AUTH-008 | Verify PIN accepts numeric values only | PIN Screen opened | Attempt non-numeric entry | A,B,C | Non-numeric values rejected | High | Rejected successfully | Pass
TC-AUTH-009 | Verify PIN length less than 4 digits | PIN Screen opened | Enter 3 digits | 123 | Input rejected | High | Rejected successfully | Pass
TC-AUTH-010 | Verify PIN length greater than 4 digits | PIN Screen opened | Enter 5 digits | 12345 | Input restricted to 4 digits | High | Restricted successfully | Pass
TC-AUTH-011 | Verify Delete button functionality | PIN Screen opened | Enter digits then Delete | 1234 | Last digit removed | Medium | Digit removed correctly | Pass
TC-AUTH-012 | Verify Return Card navigation | PIN Screen opened | Click Return Card | N/A | Session terminated successfully | Medium | Card returned successfully | Pass
TC-AUTH-013 | Verify Password Screen displayed after valid PIN | Valid PIN entered | Submit PIN | 1234 | Password Screen displayed | Critical | Screen displayed | Pass
TC-AUTH-014 | Verify successful login with valid password | Password Screen opened | Enter valid password | 1234 | User authenticated successfully | Critical | Login successful | Pass
TC-AUTH-015 | Verify invalid password error message | Password Screen opened | Enter invalid password | 9999 | ERR-002 displayed | Critical | Correct error displayed | Pass
TC-AUTH-016 | Verify password accepts numeric values only | Password Screen opened | Attempt alphabetic input | ABCD | Input rejected | High | Rejected successfully | Pass
TC-AUTH-017 | Verify password length less than 4 digits | Password Screen opened | Enter 3 digits | 123 | Input rejected | High | Rejected successfully | Pass
TC-AUTH-018 | Verify password length greater than 4 digits | Password Screen opened | Enter 5 digits | 12345 | Input restricted to 4 digits | High | Restricted successfully | Pass
TC-AUTH-019 | Verify Delete button functionality on password screen | Password Screen opened | Enter digits then Delete | 1234 | Last digit removed | Medium | Digit removed correctly | Pass
TC-AUTH-020 | Verify successful authentication navigates to Account Selection Screen | Valid credentials entered | Submit login | PIN=1234 Password=1234 | Account Selection Screen displayed | Critical | Screen displayed successfully | Pass

## Account Selection
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-ACC-001 | Verify Account Selection Screen is displayed after successful login | Valid PIN and Password | Login successfully | User Account | Account Selection Screen displayed | High | Screen displayed successfully | Pass
TC-ACC-002 | Verify account number is displayed for each account | User owns accounts | Login and open Account Selection | Current Account 100015 | Account number displayed correctly | High | Account number displayed correctly | Pass
TC-ACC-003 | Verify account type is displayed for each account | User owns accounts | Login and open Account Selection | Current / Saving / Gold | Account type displayed correctly | High | Account type displayed correctly | Pass
TC-ACC-004 | Verify Current Account is displayed when available | User has Current Account | Open Account Selection | Current Account | Current Account displayed | High | Displayed successfully | Pass
TC-ACC-005 | Verify Saving Account is displayed when available | User has Saving Account | Open Account Selection | Saving Account | Saving Account displayed | Medium | Displayed successfully | Pass
TC-ACC-006 | Verify Gold Account is displayed when available | User has Gold Account | Open Account Selection | Gold Account | Gold Account displayed | Medium | Displayed successfully | Pass
TC-ACC-007 | Verify user can select Current Account | Current Account exists | Select Current Account | Current Account | Transaction Menu displayed | High | Transaction Menu displayed | Pass
TC-ACC-008 | Verify user can select Saving Account | Saving Account exists | Select Saving Account | Saving Account | Transaction Menu displayed | High | Transaction Menu displayed | Pass
TC-ACC-009 | Verify user can select Gold Account | Gold Account exists | Select Gold Account | Gold Account | Transaction Menu displayed | High | Transaction Menu displayed | Pass
TC-ACC-010 | Verify user having one account only | User owns Current Account only | Login | Current Account | One account displayed correctly | Medium | Displayed correctly | Pass
TC-ACC-011 | Verify user having maximum three accounts | User owns 3 accounts | Login | Current + Saving + Gold | All accounts displayed | Medium | Displayed correctly | Pass
TC-ACC-012 | Verify selected account information is loaded correctly | Multiple accounts exist | Select account | Gold Account | Selected account details loaded | High | Loaded correctly | Pass

## Transaction Menu
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-MENU-001 | Verify Transaction Menu screen appears after account selection | Account selected | Select account | Gold Account | Transaction Menu displayed | High | Displayed successfully | Pass
TC-MENU-002 | Verify Last Five Transactions option displayed | Open Transaction Menu | Check menu options | N/A | Option displayed | High | Displayed successfully | Pass
TC-MENU-003 | Verify Withdraw Funds option displayed | Open Transaction Menu | Check menu options | N/A | Option displayed | High | Displayed successfully | Pass
TC-MENU-004 | Verify Deposit Funds option displayed | Open Transaction Menu | Check menu options | N/A | Option displayed | High | Displayed successfully | Pass
TC-MENU-005 | Verify Transfer Funds option displayed | Open Transaction Menu | Check menu options | N/A | Option displayed | High | Displayed successfully | Pass
TC-MENU-006 | Verify Change Password option displayed | Open Transaction Menu | Check menu options | N/A | Option displayed | High | Displayed successfully | Pass
TC-MENU-007 | Verify Select Another Account option displayed | Open Transaction Menu | Check menu options | N/A | Option displayed | Medium | Displayed successfully | Pass
TC-MENU-008 | Verify navigation to Last Five Transactions screen | Select option | Click Last Five Transactions | N/A | SCR-07 opened | High | Opened successfully | Pass
TC-MENU-009 | Verify navigation to Withdraw screen | Select option | Click Withdraw Funds | N/A | SCR-08 opened | Critical | Opened successfully | Pass
TC-MENU-010 | Verify navigation to Deposit screen | Select option | Click Deposit Funds | N/A | SCR-10 opened | Critical | Opened successfully | Pass
TC-MENU-011 | Verify navigation to Transfer screen | Select option | Click Transfer Funds | N/A | SCR-12 opened | Critical | Opened successfully | Pass
TC-MENU-012 | Verify navigation to Change Password screen | Select option | Click Change Password | N/A | SCR-15 opened | Critical | Opened successfully | Pass
TC-MENU-013 | Verify Select Another Account returns to Account Selection screen | Multiple accounts exist | Click Select Another Account | N/A | SCR-05 displayed | High | Displayed successfully | Pass

## Last Five Transactions
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-HIS-001 | Verify Transaction History screen is displayed | Account selected | Select Last Five Transactions | N/A | SCR-07 displayed | High | Displayed successfully | Pass
TC-HIS-002 | Verify account number displayed | Transaction History screen open | View page | Account 100015 | Account number displayed | High | Displayed correctly | Pass
TC-HIS-003 | Verify current balance displayed | Transaction History screen open | View page | Balance 4000 | Balance displayed correctly | High | Displayed correctly | Pass
TC-HIS-004 | Verify exactly five transactions displayed | More than 5 transactions exist | Open History | Account Transactions | Exactly 5 records displayed | Critical | 5 records displayed | Pass
TC-HIS-005 | Verify transaction number displayed | Open History | View transaction list | N/A | Transaction Number displayed | Medium | Displayed correctly | Pass
TC-HIS-006 | Verify transaction ID displayed | Open History | View transaction list | N/A | Transaction ID displayed | Medium | Displayed correctly | Pass
TC-HIS-007 | Verify transaction type displayed | Open History | View transaction list | Transfer | Transaction type displayed | Medium | Displayed correctly | Pass
TC-HIS-008 | Verify transaction amount displayed | Open History | View transaction list | 170 | Amount displayed correctly | High | Displayed correctly | Pass
TC-HIS-009 | Verify transaction date displayed | Open History | View transaction list | 2026-06-18 | Date displayed correctly | High | Displayed correctly | Pass
TC-HIS-010 | Verify transactions sorted by latest date | More than 5 transactions exist | Open History | Multiple dates | Latest transactions shown first | High | Sorted correctly | Pass
TC-HIS-011 | Verify Daily Interest displayed for Gold Account | Gold Account selected | Open History | Gold Account | Daily Interest displayed | Medium | Displayed correctly | Pass
TC-HIS-012 | Verify Daily Interest displayed for Saving Account | Saving Account selected | Open History | Saving Account | Daily Interest displayed | Medium | Displayed correctly | Pass
TC-HIS-013 | Verify Daily Interest not displayed for Current Account | Current Account selected | Open History | Current Account | Daily Interest hidden | Medium | Hidden correctly | Pass
TC-HIS-014 | Verify Print button displayed | Open History | View screen | N/A | Print button displayed | Medium | Displayed correctly | Pass
TC-HIS-015 | Verify Print operation works successfully | Printer available | Click Print | N/A | Transaction receipt/history printed | Medium | Printed successfully | Pass
TC-HIS-016 | Verify Back button returns to Transaction Menu | History screen open | Click Back | N/A | SCR-06 displayed | Medium | Returned successfully | Pass

## withdraw
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-WD-001 | Verify Withdraw option opens Withdraw Screen | User logged in and account selected | Select Withdraw Funds | N/A | Withdraw Screen displayed | Critical | Screen displayed successfully | Pass
TC-WD-002 | Verify quick withdrawal amounts are displayed | Withdraw Screen open | View quick links | 100200300 | Quick amounts displayed | High | Displayed correctly | Pass
TC-WD-003 | Verify withdrawal amount can be increased by 100 | Withdraw Screen open | Increase amount | 100→200 | Amount increased by 100 | High | Increased correctly | Pass
TC-WD-004 | Verify withdrawal amount can be decreased by 100 | Amount >100 selected | Decrease amount | 300→200 | Amount decreased by 100 | High | Decreased correctly | Pass
TC-WD-005 | Verify minimum withdrawal amount is 100 | Withdraw Screen open | Select amount below 100 | 50 | Amount rejected | Critical | Validation displayed | Pass
TC-WD-006 | Verify withdrawal amount follows increment rule | Withdraw Screen open | Attempt invalid increment | 150 | Amount rejected | Critical | Validation displayed | Pass
TC-WD-007 | Verify withdrawal amount equal to account balance | Balance available | Withdraw full balance | Balance=1000, Withdraw=1000 | Transaction allowed | Critical | Allowed successfully | Pass
TC-WD-008 | Verify withdrawal amount less than account balance | Balance available | Withdraw amount | Balance=1000, Withdraw=500 | Transaction allowed | Critical | Allowed successfully | Pass
TC-WD-009 | Verify withdrawal amount greater than account balance | Balance available | Withdraw amount | Balance=500, Withdraw=1000 | ERR-003 displayed | Critical | Error displayed correctly | Pass
TC-WD-010 | Verify confirmation page displayed | Valid amount selected | Click Enter | Amount=300 | Confirmation page displayed | Critical | Displayed successfully | Pass
TC-WD-011 | Verify selected amount displayed on confirmation page | Confirmation page open | View amount | 300 | Correct amount displayed | High | Displayed correctly | Pass
TC-WD-012 | Verify Yes button confirms withdrawal | Confirmation page open | Click Yes | Amount=300 | Withdrawal processed | Critical | Processed successfully | Pass
TC-WD-013 | Verify cash is dispensed after confirmation | Withdrawal confirmed | Click Yes | Amount=300 | ATM dispenses cash | Critical | Cash dispensed | Pass
TC-WD-014 | Verify balance updated after successful withdrawal | Successful withdrawal | Check balance | Balance=1000, Withdraw=300 | New Balance=700 | Critical | Updated correctly | Pass
TC-WD-015 | Verify transaction record created after withdrawal | Successful withdrawal | View transactions | Amount=300 | Withdrawal transaction recorded | Critical | Recorded successfully | Pass
TC-WD-016 | Verify success message displayed after withdrawal | Withdrawal completed | View result | N/A | Success message displayed | Medium | Displayed correctly | Pass
TC-WD-017 | Verify Perform Another Transaction button works | Success page displayed | Click button | N/A | Transaction Menu displayed | Medium | Returned successfully | Pass
TC-WD-018 | Verify Return Card button works | Success page displayed | Click Return Card | N/A | PIN Screen displayed | Medium | Returned successfully | Pass
TC-WD-019 | Verify No button cancels withdrawal | Confirmation page open | Click No | Amount=300 | Transaction cancelled | High | Cancelled successfully | Pass
TC-WD-020 | Verify No button returns user to Transaction Menu | Confirmation page open | Click No | N/A | Transaction Menu displayed | High | Returned successfully | Pass

## deposit
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-DP-001 | Verify Deposit option opens Deposit Screen | User logged in | Select Deposit Funds | N/A | Deposit Screen displayed | Critical | Displayed successfully | Pass
TC-DP-002 | Verify numeric keyboard displayed | Deposit Screen open | View keyboard | N/A | Numeric keyboard displayed | High | Displayed correctly | Pass
TC-DP-003 | Verify deposit amount accepts numeric values | Deposit Screen open | Enter amount | 500 | Amount accepted | High | Accepted successfully | Pass
TC-DP-004 | Verify minimum deposit amount validation | Deposit Screen open | Enter amount | 5 | Validation error displayed | Critical | Error displayed | Pass
TC-DP-005 | Verify minimum deposit amount accepted | Deposit Screen open | Enter amount | 10 | Amount accepted | Critical | Accepted successfully | Pass
TC-DP-006 | Verify large deposit amount accepted | Deposit Screen open | Enter amount | 100000 | Amount accepted | Medium | Accepted successfully | Pass
TC-DP-007 | Verify confirmation page displayed | Valid amount entered | Click Enter | 500 | Confirmation page displayed | High | Displayed successfully | Pass
TC-DP-008 | Verify deposit amount displayed on confirmation page | Confirmation page open | View amount | 500 | Correct amount displayed | High | Displayed correctly | Pass
TC-DP-009 | Verify Yes button confirms deposit | Confirmation page open | Click Yes | 500 | Deposit processed | Critical | Processed successfully | Pass
TC-DP-010 | Verify balance updated after deposit | Deposit successful | Check balance | Balance=1000, Deposit=500 | Balance=1500 | Critical | Updated correctly | Pass
TC-DP-011 | Verify deposit transaction record created | Deposit successful | View transactions | Amount=500 | Deposit recorded | Critical | Recorded successfully | Pass
TC-DP-012 | Verify success message displayed | Deposit successful | View result | N/A | Success message displayed | Medium | Displayed correctly | Pass
TC-DP-013 | Verify Perform Another Transaction button works | Success page displayed | Click button | N/A | Transaction Menu displayed | Medium | Returned successfully | Pass
TC-DP-014 | Verify Return Card button works | Success page displayed | Click Return Card | N/A | PIN Screen displayed | Medium | Returned successfully | Pass
TC-DP-015 | Verify No button cancels deposit | Confirmation page open | Click No | Amount=500 | Deposit cancelled | High | Cancelled successfully | Pass
TC-DP-016 | Verify No button returns user to Transaction Menu | Confirmation page open | Click No | N/A | Transaction Menu displayed | High | Returned successfully | Pass

## Transfer
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-TR-001 | Verify Transfer option opens Receiver Screen | User logged in | Select Transfer Funds | N/A | Receiver PIN Screen displayed | Critical | Displayed successfully | Pass
TC-TR-002 | Verify receiver PIN accepts numeric values | Receiver Screen open | Enter PIN | 1234 | PIN accepted | High | Accepted successfully | Pass
TC-TR-003 | Verify valid receiver PIN | Receiver exists | Enter PIN | Valid PIN | Next screen displayed | Critical | Displayed successfully | Pass
TC-TR-004 | Verify invalid receiver PIN error message | Receiver not found | Enter PIN | 9999 | ERR-004 displayed | Critical | Displayed correctly | Pass
TC-TR-005 | Verify transfer amount screen displayed | Valid receiver entered | Continue | Receiver PIN | Amount screen displayed | High | Displayed successfully | Pass
TC-TR-006 | Verify minimum transfer amount validation | Amount screen open | Enter amount | 5 | Validation error displayed | Critical | Error displayed | Pass
TC-TR-007 | Verify minimum transfer amount accepted | Amount screen open | Enter amount | 10 | Amount accepted | Critical | Accepted successfully | Pass
TC-TR-008 | Verify transfer amount equal to balance | Balance available | Enter amount | Balance=1000 | Transfer allowed | Critical | Allowed successfully | Pass
TC-TR-009 | Verify transfer amount less than balance | Balance available | Enter amount | 500 | Transfer allowed | Critical | Allowed successfully | Pass
TC-TR-010 | Verify transfer amount greater than balance | Balance=500 | Enter amount | 1000 | ERR-003 displayed | Critical | Displayed correctly | Pass
TC-TR-011 | Verify confirmation page displayed | Valid amount entered | Click Enter | 100 | Confirmation page displayed | Critical | Displayed successfully | Pass
TC-TR-012 | Verify receiver name displayed on confirmation page | Confirmation page open | View page | Amr Gamal | Receiver name displayed | High | Displayed correctly | Pass
TC-TR-013 | Verify transfer amount displayed on confirmation page | Confirmation page open | View page | 100 | Correct amount displayed | High | Displayed correctly | Pass
TC-TR-014 | Verify Yes button confirms transfer | Confirmation page open | Click Yes | 100 | Transfer processed | Critical | Processed successfully | Pass
TC-TR-015 | Verify sender balance updated after transfer | Transfer successful | Check balance | Balance=1000, Transfer=100 | Balance=900 | Critical | Updated correctly | Pass
TC-TR-016 | Verify receiver balance updated after transfer | Transfer successful | Check receiver account | Amount=100 | Receiver balance increased | Critical | Updated correctly | Pass
TC-TR-017 | Verify transfer transaction record created | Transfer successful | View transactions | Amount=100 | Transaction recorded | Critical | Recorded successfully | Pass
TC-TR-018 | Verify success message displayed | Transfer successful | View result | N/A | Success message displayed | Medium | Displayed correctly | Pass
TC-TR-019 | Verify Perform Another Transaction button works | Success page displayed | Click button | N/A | Transaction Menu displayed | Medium | Returned successfully | Pass
TC-TR-020 | Verify Return Card button works | Success page displayed | Click Return Card | N/A | PIN Screen displayed | Medium | Returned successfully | Pass
TC-TR-021 | Verify No button cancels transfer | Confirmation page open | Click No | Amount=100 | Transfer cancelled | High | Cancelled successfully | Pass
TC-TR-022 | Verify No button returns user to Transaction Menu | Confirmation page open | Click No | N/A | Transaction Menu displayed | High | Returned successfully | Pass
TC-TR-023 | Verify transferred amount goes to receiver Current Account | Receiver has multiple accounts | Complete transfer | Amount=100 | Amount added to Current Account only | Critical | Added correctly | Pass
TC-TR-024 | Verify transfer from Gold Account to another user | Gold Account selected | Transfer funds | Amount=100 | Transfer completed successfully | Critical | Completed successfully | Pass
TC-TR-025 | Verify transfer from Saving Account to another user | Saving Account selected | Transfer funds | Amount=100 | Transfer completed successfully | Critical | Completed successfully | Pass
TC-TR-026 | Verify transfer from Gold/Saving to own Current Account (Open Question) | User owns multiple accounts | Attempt transfer | Own Current Account | Behavior depends on business decision (OQ-01) | Medium | Pending Business Decision | N/A | OQ-01

## Change Password
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-CP-001 | Verify Change Password screen is displayed | User logged in | Open Change Password option | N/A | Change Password screen displayed successfully | High | Screen displayed successfully | Pass
TC-CP-002 | Verify current password validation with valid password | User logged in | Enter correct current password | Current Password = 1234 | System accepts password and proceeds to next step | Critical | Password accepted | Pass
TC-CP-003 | Verify current password validation with invalid password | User logged in | Enter incorrect current password | Current Password = 9999 | Error message ERR-002 displayed | Critical | Error displayed correctly | Pass
TC-CP-004 | Verify new password accepts exactly 4 digits | User logged in | Enter new password | 5678 | System accepts password | High | Password accepted | Pass
TC-CP-005 | Verify new password rejects less than 4 digits | User logged in | Enter new password | 123 | Password rejected | High | Password rejected | Pass
TC-CP-006 | Verify new password rejects more than 4 digits | User logged in | Enter new password | 12345 | Password rejected | High | Password rejected | Pass
TC-CP-007 | Verify new password accepts numeric values only | User logged in | Enter alphabetic password | ABCD | Password rejected | High | Password rejected | Pass
TC-CP-008 | Verify user cannot reuse current password | User logged in | Enter same password as current password | Current=1234 New=1234 | ERR-006 displayed | Critical | Error displayed correctly | Pass
TC-CP-009 | Verify confirm password matches new password | User logged in | Enter matching confirmation password | New=5678 Confirm=5678 | Password updated successfully | Critical | Password updated | Pass
TC-CP-010 | Verify mismatch confirmation password | User logged in | Enter different confirmation password | New=5678 Confirm=8765 | ERR-005 displayed | Critical | Error displayed correctly | Pass
TC-CP-011 | Verify password update after successful change | User logged in | Complete password change process | New Password = 5678 | Password updated in system | Critical | Password updated | Pass
TC-CP-012 | Verify login using newly updated password | Password changed | Login again | New Password = 5678 | Login successful | Critical | Login successful | Pass

## Transaction Recording
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-TR-001 | Verify transaction record created after successful withdrawal | Successful withdrawal | Perform withdrawal | Amount=100 | Transaction record created | Critical | Record created | Pass
TC-TR-002 | Verify transaction record created after successful deposit | Successful deposit | Perform deposit | Amount=500 | Transaction record created | Critical | Record created | Pass
TC-TR-003 | Verify transaction record created after successful transfer | Successful transfer | Perform transfer | Amount=100 | Transaction record created | Critical | Record created | Pass
TC-TR-004 | Verify unique transaction ID generation | Transaction executed | Check transaction record | N/A | Unique transaction ID generated | High | Unique ID generated | Pass
TC-TR-005 | Verify transaction timestamp storage | Transaction executed | Check transaction record | N/A | Correct timestamp stored | High | Timestamp stored correctly | Pass
TC-TR-006 | Verify transaction type stored correctly | Transaction executed | Check transaction record | Withdrawal | Type stored correctly | High | Stored correctly | Pass
TC-TR-007 | Verify transaction amount stored correctly | Transaction executed | Check transaction record | Amount=500 | Amount stored correctly | High | Stored correctly | Pass
TC-TR-008 | Verify failed transaction is not recorded as successful | Failed withdrawal | Execute withdrawal exceeding balance | Amount=10000 | No successful transaction record created | Critical | No record created | Pass
TC-TR-009 | Verify transaction linked to selected account | User has multiple accounts | Execute transaction | Gold Account | Transaction linked to selected account | High | Linked correctly | Pass
TC-TR-010 | Verify multiple transactions maintain unique IDs | Execute multiple transactions | Deposit, Withdraw, Transfer | Various amounts | Every transaction has unique ID | High | IDs unique | Pass

## Error Handing
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-EH-001 | Verify Invalid PIN error message | Login page opened | Enter invalid PIN | 9999 | ERR-001 displayed | Critical | Error displayed correctly | Pass
TC-EH-002 | Verify Invalid Password error message | Valid PIN entered | Enter invalid password | 9999 | ERR-002 displayed | Critical | Error displayed correctly | Pass
TC-EH-003 | Verify insufficient balance during withdrawal | Logged in | Withdraw amount greater than balance | Balance=500 Amount=1000 | ERR-003 displayed | Critical | Error displayed correctly | Pass
TC-EH-004 | Verify invalid receiver account during transfer | Logged in | Enter invalid receiver PIN | 9999 | ERR-004 displayed | Critical | Error displayed correctly | Pass
TC-EH-005 | Verify password mismatch error | Change Password screen | Enter mismatching confirmation password | New=1234 Confirm=5678 | ERR-005 displayed | Critical | Error displayed correctly | Pass
TC-EH-006 | Verify same password error | Change Password screen | Enter same current and new password | 1234 | ERR-006 displayed | Critical | Error displayed correctly | Pass
TC-EH-007 | Verify API connection failure handling during balance retrieval | API unavailable | Request account balance | N/A | ERR-007 displayed | Critical | Error displayed correctly | Pass
TC-EH-008 | Verify API connection failure handling during withdrawal | API unavailable | Execute withdrawal | Amount=100 | ERR-007 displayed | Critical | Error displayed correctly | Pass
TC-EH-009 | Verify API connection failure handling during deposit | API unavailable | Execute deposit | Amount=500 | ERR-007 displayed | Critical | Error displayed correctly | Pass
TC-EH-010 | Verify API connection failure handling during transfer | API unavailable | Execute transfer | Amount=100 | ERR-007 displayed | Critical | Error displayed correctly | Pass
TC-EH-011 | Verify transaction processing failure during withdrawal | Transaction service failure | Execute withdrawal | Amount=100 | ERR-008 displayed | Critical | Error displayed correctly | Pass
TC-EH-012 | Verify transaction processing failure during deposit | Transaction service failure | Execute deposit | Amount=500 | ERR-008 displayed | Critical | Error displayed correctly | Pass
TC-EH-013 | Verify transaction processing failure during transfer | Transaction service failure | Execute transfer | Amount=100 | ERR-008 displayed | Critical | Error displayed correctly | Pass
TC-EH-014 | Verify system prevents transaction completion after error | Error generated | Continue process | N/A | Transaction not completed | Critical | Transaction blocked | Pass
TC-EH-015 | Verify user can retry operation after error | Error generated | Retry operation | Valid data | Transaction proceeds normally | High | Retry successful | Pass

## Input Validation
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-IV-001 | Verify PIN accepts exactly 4 digits | PIN Screen displayed | Enter valid PIN | 1234 | PIN accepted | High | PIN accepted | Pass
TC-IV-002 | Verify PIN rejects less than 4 digits | PIN Screen displayed | Enter PIN | 123 | Validation error displayed | High | Validation displayed | Pass
TC-IV-003 | Verify PIN rejects more than 4 digits | PIN Screen displayed | Enter PIN | 12345 | Extra digit not accepted | High | Validation enforced | Pass
TC-IV-004 | Verify PIN accepts numeric values only | PIN Screen displayed | Enter alphabetic characters | ABCD | Input rejected | High | Input rejected | Pass
TC-IV-005 | Verify Password accepts exactly 4 digits | Password Screen displayed | Enter password | 5678 | Password accepted | High | Password accepted | Pass
TC-IV-006 | Verify Password rejects less than 4 digits | Password Screen displayed | Enter password | 567 | Validation error displayed | High | Validation displayed | Pass
TC-IV-007 | Verify Password rejects more than 4 digits | Password Screen displayed | Enter password | 56789 | Extra digit rejected | High | Validation enforced | Pass
TC-IV-008 | Verify Password accepts numeric values only | Password Screen displayed | Enter characters | ABCD | Input rejected | High | Input rejected | Pass
TC-IV-009 | Verify withdrawal amount equals minimum value | Withdrawal Screen displayed | Select amount | 100 | Amount accepted | High | Amount accepted | Pass
TC-IV-010 | Verify withdrawal amount below minimum value | Withdrawal Screen displayed | Select amount | 50 | Transaction rejected | Critical | Transaction rejected | Pass
TC-IV-011 | Verify withdrawal amount follows increment rule | Withdrawal Screen displayed | Select amount | 250 | Transaction rejected | Critical | Transaction rejected | Pass
TC-IV-012 | Verify withdrawal amount cannot exceed balance | Balance available | Withdraw amount | Balance=500, Amount=600 | ERR-003 displayed | Critical | Error displayed | Pass
TC-IV-013 | Verify deposit amount equals minimum value | Deposit Screen displayed | Enter amount | 10 | Deposit accepted | High | Deposit accepted | Pass
TC-IV-014 | Verify deposit amount below minimum value | Deposit Screen displayed | Enter amount | 5 | Deposit rejected | High | Deposit rejected | Pass
TC-IV-015 | Verify large deposit amount | Deposit Screen displayed | Enter amount | 999999 | Deposit accepted | Medium | Deposit accepted | Pass
TC-IV-016 | Verify transfer amount equals minimum value | Transfer Screen displayed | Enter amount | 10 | Transfer accepted | High | Transfer accepted | Pass
TC-IV-017 | Verify transfer amount below minimum value | Transfer Screen displayed | Enter amount | 5 | Transfer rejected | High | Transfer rejected | Pass
TC-IV-018 | Verify transfer amount exceeds balance | Transfer Screen displayed | Enter amount | Balance=100, Amount=500 | ERR-003 displayed | Critical | Error displayed | Pass
TC-IV-019 | Verify account number accepts numeric values only | Transfer Screen displayed | Enter account number | ABC123 | Input rejected | High | Input rejected | Pass
TC-IV-020 | Verify mandatory fields cannot be left empty | Any transaction screen | Leave field blank and submit | Empty value | Validation message displayed | High | Validation displayed | Pass

## security
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-SEC-001 | Verify only valid PIN can access system | Login screen displayed | Enter invalid PIN | 9999 | Access denied | Critical | Access denied | Pass
TC-SEC-002 | Verify only valid password can access system | Password screen displayed | Enter invalid password | 9999 | Access denied | Critical | Access denied | Pass
TC-SEC-003 | Verify unauthorized user cannot access accounts | Login screen displayed | Skip authentication | N/A | Access denied | Critical | Access denied | Pass
TC-SEC-004 | Verify user can access only own accounts | User logged in | View account list | N/A | Own accounts only displayed | Critical | Accounts filtered correctly | Pass
TC-SEC-005 | Verify PIN is masked during entry | PIN Screen displayed | Enter PIN | 1234 | Digits hidden | High | Digits hidden | Pass
TC-SEC-006 | Verify Password is masked during entry | Password Screen displayed | Enter password | 1234 | Digits hidden | High | Digits hidden | Pass
TC-SEC-007 | Verify transaction cannot be executed without authentication | ATM launched | Attempt transaction directly | N/A | Access denied | Critical | Access denied | Pass
TC-SEC-008 | Verify direct URL/screen navigation is blocked | User not authenticated | Open protected screen | SCR-06 | Redirect to login | High | Redirected | Pass
TC-SEC-009 | Verify SQL Injection attempt in PIN field | PIN Screen displayed | Enter SQL payload | ' OR 1=1 -- | Login rejected | Critical | Login rejected | Pass
TC-SEC-010 | Verify SQL Injection attempt in Password field | Password Screen displayed | Enter SQL payload | ' OR 1=1 -- | Login rejected | Critical | Login rejected | Pass
TC-SEC-011 | Verify transaction records cannot be modified by customer | Logged in | Attempt record modification | N/A | Modification denied | High | Modification denied | Pass
TC-SEC-012 | Verify user data privacy protection | Logged in | View another customer's data | N/A | Access denied | Critical | Access denied | Pass
TC-SEC-013 | Verify transfer to unauthorized account is blocked | Logged in | Transfer to invalid account | Invalid Receiver | ERR-004 displayed | Critical | Error displayed | Pass
TC-SEC-014 | Verify session remains authenticated during transaction flow | Logged in | Perform transactions | N/A | Session maintained | Medium | Session maintained | Pass
TC-SEC-015 | Verify sensitive information not displayed in error messages | Trigger error | Generate error | N/A | Generic secure message displayed | High | Secure message displayed | Pass

## Performance
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-PER-001 | Verify Welcome Screen load time | ATM started | Open system | N/A | Screen displayed within 3 seconds | Medium | 1.2 sec | Pass
TC-PER-002 | Verify Help Screen response time | Welcome Screen displayed | Click Help | N/A | Screen displayed within 3 seconds | Medium | 0.9 sec | Pass
TC-PER-003 | Verify PIN validation response time | Login screen displayed | Submit valid PIN | 1234 | Validation completed within 3 seconds | Medium | 1.1 sec | Pass
TC-PER-004 | Verify Password validation response time | Password screen displayed | Submit password | 1234 | Validation completed within 3 seconds | Medium | 1.0 sec | Pass
TC-PER-005 | Verify account retrieval performance | User authenticated | Open Account Selection | N/A | Accounts loaded within 3 seconds | Medium | 1.4 sec | Pass
TC-PER-006 | Verify transaction menu load performance | Account selected | Open menu | N/A | Menu loaded within 3 seconds | Medium | 0.8 sec | Pass
TC-PER-007 | Verify last five transactions retrieval performance | Logged in | View transaction history | N/A | Data loaded within 3 seconds | Medium | 1.6 sec | Pass
TC-PER-008 | Verify withdrawal processing performance | Logged in | Withdraw amount | 100 | Transaction completed within 3 seconds | Medium | 2.0 sec | Pass
TC-PER-009 | Verify deposit processing performance | Logged in | Deposit amount | 500 | Transaction completed within 3 seconds | Medium | 1.8 sec | Pass
TC-PER-010 | Verify transfer processing performance | Logged in | Transfer amount | 100 | Transaction completed within 3 seconds | Medium | 2.2 sec | Pass
TC-PER-011 | Verify password change performance | Logged in | Change password | 5678 | Password updated within 3 seconds | Medium | 1.5 sec | Pass
TC-PER-012 | Verify API balance retrieval performance | API connected | Request balance | N/A | Response within 3 seconds | Medium | 1.3 sec | Pass
TC-PER-013 | Verify API withdrawal processing performance | API connected | Withdraw funds | 100 | Response within 3 seconds | Medium | 2.1 sec | Pass
TC-PER-014 | Verify API transfer processing performance | API connected | Transfer funds | 100 | Response within 3 seconds | Medium | 2.4 sec | Pass
TC-PER-015 | Verify system stability during continuous usage | System running | Execute transactions continuously | 100 operations | No crash or failure occurs | Medium | Stable | Pass

## Relaibility
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-RL-001 | Verify ATM system availability after startup | ATM launched | Start application | N/A | System becomes available successfully | Medium | System available | Pass
TC-RL-002 | Verify customer can perform multiple consecutive transactions | User logged in | Perform Deposit, Withdraw, Transfer sequentially | Various amounts | All transactions completed successfully | Medium | Transactions completed | Pass
TC-RL-003 | Verify transaction history remains available after multiple operations | User completed transactions | Open Last Five Transactions screen | N/A | Transaction history displayed correctly | Medium | History displayed | Pass
TC-RL-004 | Verify system recovers after temporary API interruption | API temporarily unavailable | Restore API connection | N/A | System resumes normal operation | Medium | System recovered | Pass
TC-RL-005 | Verify withdrawal failure does not crash application | Logged in | Force withdrawal processing error | Amount=100 | Error handled gracefully | Medium | Error handled | Pass
TC-RL-006 | Verify deposit failure does not crash application | Logged in | Force deposit processing error | Amount=500 | Error handled gracefully | Medium | Error handled | Pass
TC-RL-007 | Verify transfer failure does not crash application | Logged in | Force transfer processing error | Amount=100 | Error handled gracefully | Medium | Error handled | Pass
TC-RL-008 | Verify invalid PIN attempts do not affect system stability | Login screen displayed | Enter invalid PIN repeatedly | 9999 | System remains operational | Medium | System stable | Pass
TC-RL-009 | Verify invalid password attempts do not affect system stability | Password screen displayed | Enter invalid password repeatedly | 9999 | System remains operational | Medium | System stable | Pass
TC-RL-010 | Verify system maintains data consistency after failed withdrawal | Balance=500 | Withdraw 1000 | Amount=1000 | Balance remains unchanged | High | Balance unchanged | Pass
TC-RL-011 | Verify system maintains data consistency after failed transfer | Balance=100 | Transfer 500 | Amount=500 | No funds transferred | High | No transfer occurred | Pass
TC-RL-012 | Verify successful transaction data persists after restart | Successful transaction executed | Restart system | N/A | Transaction remains stored | High | Data persisted | Pass
TC-RL-013 | Verify account balances persist after restart | Existing accounts available | Restart system | N/A | Balances remain accurate | High | Balances preserved | Pass
TC-RL-014 | Verify application restart time does not exceed 30 seconds | ATM running | Restart application | N/A | Restart completed within 30 seconds | Medium | 18 seconds | Pass
TC-RL-015 | Verify ATM remains operational after prolonged usage | System running | Execute operations continuously | 100+ operations | No crash or abnormal behavior | Medium | Stable operation | Pass

## Usability
Test Case ID | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Priority | Actual Result | Result | Comments
TC-US-001 | Verify Welcome Screen is understandable for first-time user | ATM launched | Observe welcome screen | N/A | User can understand available actions | Low | Easy to understand | Pass
TC-US-002 | Verify Login button is clearly visible | Welcome Screen displayed | Inspect screen | N/A | Login button visible and accessible | Low | Visible | Pass
TC-US-003 | Verify Help button is clearly visible | Welcome Screen displayed | Inspect screen | N/A | Help button visible and accessible | Low | Visible | Pass
TC-US-004 | Verify Help screen provides sufficient instructions | Help screen opened | Read instructions | N/A | User understands ATM operation process | Medium | Instructions clear | Pass
TC-US-005 | Verify Back button functionality on Help screen | Help screen displayed | Click Back | N/A | User returned to Welcome Screen | Medium | Returned successfully | Pass
TC-US-006 | Verify navigation between screens is intuitive | Logged in | Navigate through menus | N/A | User completes tasks without confusion | Medium | Navigation clear | Pass
TC-US-007 | Verify account information is displayed clearly | Account Selection screen displayed | View accounts | N/A | Account type and number readable | Medium | Information clear | Pass
TC-US-008 | Verify transaction menu options are clearly labeled | Transaction Menu displayed | Review options | N/A | User understands each option | Medium | Labels clear | Pass
TC-US-009 | Verify confirmation screens clearly explain selected action | Withdrawal/Deposit/Transfer confirmation screen displayed | Review message | N/A | Confirmation message understandable | Medium | Message clear | Pass
TC-US-010 | Verify success messages are clear and informative | Successful transaction completed | Review success screen | N/A | User understands transaction completed successfully | Medium | Message clear | Pass
TC-US-011 | Verify error messages are understandable | Trigger error | Invalid PIN | N/A | User understands what went wrong | Medium | Error understandable | Pass
TC-US-012 | Verify interface language is formal and polite | Navigate system | Review screen text | N/A | Language follows business standards | Low | Language appropriate | Pass
TC-US-013 | Verify keypad buttons are easy to use | PIN/Password screen displayed | Use keypad | N/A | User can enter data easily | Medium | Keypad usable | Pass
TC-US-014 | Verify transaction completion requires minimal user effort | Logged in | Perform withdrawal | Amount=100 | Transaction completed with few steps | Medium | Efficient process | Pass
TC-US-015 | Verify currency values are displayed clearly | Account/Transaction screens displayed | Review amounts | N/A | Currency values clearly visible and readable | Low | Clearly displayed | Pass